## New Navigation
Title | Old URL | New URL | Old Link | Status | ETA | Column 1 | Peace at Home Website Sitemap + Page Direction
Home | peaceathomeparenting.com | https://pahp.underdogdigitalwebsite.com/home-new/ |  | In Review | 2026-06-29 | B2b TOP MENU
Solutions | n/a | https://pahp.underdogdigitalwebsite.com/solutions/ |  | Completed |  | B2b TOP MENU |  | Comments on the Solutions Page
Employers | https://peaceathomeparenting.com/corporate/ | https://pahp.underdogdigitalwebsite.com/corporate/ | Old Link | Completed | 2026-07-06 | B2B Sub page |  | Video needs to be a B2B (about us in on home page - portal is on resources)
Universities & Colleges | https://peaceathomeparenting.com/college-mental-health/ | https://pahp.underdogdigitalwebsite.com/college-mental-health/?fsdfsd | Old Link | Completed | 2026-07-06 | B2B Sub page | Love the redo | what's included - need to add progrms change resrouce guides to OnDemand Resources
K-12 Schools | https://peaceathomeparenting.com/school/ | https://pahp.underdogdigitalwebsite.com/school/ | Old Link | Completed | 2026-07-06 | B2B Sub page | consistency of componets - lets confirm | logos
Family Service Organizations | https://peaceathomeparenting.com/np/ |  | Old Link | Request | 2026-07-06 | B2B Sub page |  | MENU
Parents | https://peaceathomeparenting.com/getting-started/ (and sub pages on menu) | n/a |  | Request | n/a | B2B Sub page |  | Services Menu - no drop down?
Live Calendar | https://peaceathomeparenting.com/calendar/ | sub page of Parents | [5 empty] | if keeping it - KW provide new list
RESOURCES |  | https://pahp.underdogdigitalwebsite.com/resource-page/ |  | In Progress |  | B2b TOP MENU | Trello Card with Edits | about - drop down - our experts
Section 3 & 4 By Age & By Family Matters - Programs Page | use a template interactive workshop page for this | [6 empty] | soluitions - change the menu items
Workshops | https://peaceathomeparenting.com/custom-interactive-workshops/
Discussions | https://peaceathomeparenting.com/discussions-with-an-expert-recorded/
Professional Development | https://peaceathomeparenting.com/courses/professional-development-workshops/
On Demand - Resource Guide Sample | https://peaceathomeparenting.com/resource-page-main/ | static version of parent one (link to each of the features - sample)
On Demand Quick Videos (LD Courses) | https://peaceathomeparenting.com/partner-library/
On Demand - Blogs | https://peaceathomeparenting.com/expert-blog/
On Demand - Podcasts | Link to Spotify
Quick Tips (LD Course) | https://peaceathomeparenting.com/parenting-quick-tips/ |  |  | Request | 2026-07-06
Break the Screen Cycle | https://peaceathomeparenting.com/break-the-sceen-cycle-reclaim-connection-calm/ | could be on bottom - tbd - see more content |  | Request | 2026-07-06
1:1 Consulitng | https://peaceathomeparenting.com/11-consultation/
Newsletter (Parent one) | https://peaceathomeparenting.com/handouts-pah-newsletters/ |  |  | Request | 2026-07-06
ABOUT |  | https://pahp.underdogdigitalwebsite.com/about-us/ |  | Completed |  | B2b TOP MENU
Our Experts | https://peaceathomeparenting.com/our-experts/
Contact | https://peaceathomeparenting.com/concierge/ | https://pahp.underdogdigitalwebsite.com/contact |  | Request | 2026-07-06 | B2b TOP MENU
button on the resource page - check out content | What do we do with Search? Parents and Users needed it - think it's good for sales - where should it go
where are the logos and testimonirals ? Home has testimonails
are we putting logos on indivvidual pages?
LD and what's not | B2B section - only LD - quick vidoes - all esle pages - sample Resource Guide etc | QV log in
All can have the B2B Menu
consistency of componets on the sales pages

## Portal
Column 6 | Title | URL | New URL | Notes | Status | ETA | registratrion Link | Code | Column 1
| Portal | https://pahp.underdogdigitalwebsite.com/portal-new/ |  | Template | In Progress | 2026-06-29 |  |  | Portal page needs to be able to be branded room for client lgoo
| Portal - Annual Sub | https://pahp.underdogdigitalwebsite.com/peace-at-home-parenting-portal/ |  | one for many | Request | 2026-07-01 |  |  | Ruth Also Wants the PAH portal image up front (on current )
| Portal - College Mental Health | https://pahp.underdogdigitalwebsite.com/portal-college-mh/ |  | one for many | Request | 2026-07-01 |  |  | Feel like the first section is too big - takes up entire fold - PAH colors warmer
| Portal - K-12 | https://peaceathomeparenting.com/portal-k-12-school/ |  | one for many |  |  |  |  | PORTAL EDITS
| Portal- Early Childhood | kath find link |  | one for many |  |  |  |  | WORKSHOPS (keep it at 1 row)
| Portal - BeBio | https://pahp.underdogdigitalwebsite.com/be-biopharma-inc/ |  | Client | Request |  |  |  | Calendar
| Portal - Casa Tx | https://pahp.underdogdigitalwebsite.com/casa-for-kids-parenting-solutions-portal/ |  | Client | Request |  |  |  | Recorded
| Portal - CHN | https://pahp.underdogdigitalwebsite.com/chnct-login/ |  | Client | Request |  |  |  | RESOURCES GUIDES by Age
| Portal - Emory University | https://pahp.underdogdigitalwebsite.com/emory-university-parenting-solutions-portal/ |  | Client | Request |  |  |  | Center the 2nd Row
| Portal - Extreme Networks | https://pahp.underdogdigitalwebsite.com/portal-extreme-networks/ |  | Client | Request |  |  |  | Same title over Resources by Age and Family Matters
| Portal - Farmington | https://pahp.underdogdigitalwebsite.com/farmington-parenting-solutions-portal/ |  | Client | Request |  |  |  | Live, On-Demand, One on One Resources
| Portal - MIT | https://pahp.underdogdigitalwebsite.com/mit-login/ |  | Client | Request |  |  |  | RESOURCES GUIDES for Family Matters
| Portal - OMG | https://pahp.underdogdigitalwebsite.com/omg-working-parents-network-parenting-center/ |  | Client | Request |  |  |  | see notes on Resource guides on next tab
| Portal - South Windsor | https://pahp.underdogdigitalwebsite.com/south-windsor-login/ |  | Client | Request |  |  |  | Solutions 3 boexs over 3 boxes
| Portal - Teladoc | https://pahp.underdogdigitalwebsite.com/teladoc-parenting-center/ |  | Client | Request |  |  | top | Quick Video Libraries (Different than B2B)
| OPEN Client PAGES | template | [5 empty] | top | Quick tips
| MPY | https://peaceathomeparenting.com/mpy-solution-libraries/ |  | Client |  |  |  | top | Discussions with an expert
| Bridgewell (within an app) | https://peaceathomeparenting.com/landing-page-bridgewell/ |  | Client |  |  |  | bottom | Break the Cycle
| bridgewell client | https://peaceathomeparenting.com/bridgewell-ftl-fla/ | [5 empty] | bottom | Podcasts
| unique library page for tracking | https://peaceathomeparenting.com/library-bridgewell/ | [5 empty] | bottom | Blogs
| Husky (govt template required) | https://peaceathomeparenting.com/husky-health/ |  | Client |  |  |  |  | Community and Support 4 boxes
| spanish page | https://peaceathomeparenting.com/biblioteca-en-espanol-de-husky-health/ | [6 empty] | REmove lunch and learn - let's just keep it up in Live
| Yale | https://peaceathomeparenting.com/worklife-at-yale-university/ |  | Client |  |  |  |  | Happening This Month (newsletter link)
| Yale library pg for reporting | https://peaceathomeparenting.com/quick-video-solutions-pack/ | [6 empty] | Community Forum
| BBBS | https://peaceathomeparenting.com/landing-page-bbbs-nyc/ |  | Client |  |  |  |  | Specialists Ready to Help (Call or email )
| BBBS library pg for reporting | https://peaceathomeparenting.com/bbbs-quick-video-solutions-pack/ | [6 empty] | Search PAH
| CSO | https://peaceathomeparenting.com/landing-page-cso-frc/ |  | Client |  |  |  |  | 1:1 Consulting
| cso library pg for reporting | https://peaceathomeparenting.com/library-open-cso-frc/ | [6 empty] | Links to the expert page (B2B one but use Portal menu)

## Resource Guides
Title | URL | New URL | Status | ETA
Resoruce Guide Template | https://pahp.underdogdigitalwebsite.com/resources-peace-at-home-starts-here/ |  | Request |  | QA | These need work
Ages | [5 empty] | let's talk about what we are trying to achieve
Welcome Baby | https://pahp.underdogdigitalwebsite.com/welcome-baby/ |  | In Progress | 2026-06-29 | QA | Note we need 2 versions of each
Toddler & Preschooler | https://pahp.underdogdigitalwebsite.com/resources-toddlers-and-preschoolers/ |  | Request |  | QA | OPEN - without the recorded workshosp (OPEN CLIENTS)
School Age | https://pahp.underdogdigitalwebsite.com/resources-school-aged-kids-six-to-twelve/ |  | Request |  | QA | CLOSED - all items
Teens & Young Adults | https://pahp.underdogdigitalwebsite.com/resources-teens-tweens-young-adults/ |  | Request |  | QA
Young Adults (College Kids) | https://pahp.underdogdigitalwebsite.com/college-mental-health-resources/
Parenting Matters
Parent Well-Being | https://pahp.underdogdigitalwebsite.com/resources-peace-at-home-starts-here/ |  |  |  |  | https://pahp.underdogdigitalwebsite.com/college-mental-health-resources-2/
K-12 School Success | https://pahp.underdogdigitalwebsite.com/resources-back-to-school/ |  | Request |  | QA
Social Media & Screen Time | https://pahp.underdogdigitalwebsite.com/resources-social-media-screen-time/ |  | Request
Mental Health | https://pahp.underdogdigitalwebsite.com/resources-mental-health/ |  | Request
Neurodiversity | https://pahp.underdogdigitalwebsite.com/neurodiversity-resources/ |  | Request
Raising LGBTQ+ Kids | https://pahp.underdogdigitalwebsite.com/resources-lgbtq/ |  | Request
Spanish Language Resources | https://pahp.underdogdigitalwebsite.com/resources-spanish-language-resources/ |  | Request |  | QA

## Library
Search_Reference Live Web Blogs Podcasts_CAREFUL
Title | URL | New URL | Status | ETA

## Navigation 2.0
B2B Navigation | The public marketing site — home, solutions, resources, about, contact. |  |  | Portal Navigation | For logged-in client portals (BBBS, Yale, CSO, Emory, ~14 total). | Open Client Navigation | For open (non-login) client pages — BBBS landing, Yale open library, CSO open.
Main Page | Sub Nav | New URL | Sub URL
Home |  | https://pahp.underdogdigitalwebsite.com/home-new/ |  | Client Logo Branded per portal |  | PAH Logo | Editor picks from dropdown
Solutions |  | https://pahp.underdogdigitalwebsite.com/solutions/ |  | Resource Guides Open set OR Closed set
| Employers |  |  | Quick Video Libraries Open set OR Closed set |  | Quick Tips
| Colleges and Universities |  |  | Live Workshops |  | Break the Cycle
| K-12 |  |  | Recorded Workshops |  | Discussion with an Expert
| Childcare and Daycare Centers |  |  | Discussions with an Expert |  | Blogs
| Family Service Organizations |  |  | Consulting | Toggle — hidden if client didn't purchase | Podcasts
| Parents |  |  | Search |  | Resource Guides · Open
Services |  |  |  | Support / Contact |  | Quick Video Library · Open
| Live Workshop |  |  |  |  | How Can We Help
| On Demand Resources |  |  | Required on every portal page |  | Contact Us
| Consulting |  |  | Client logo (branded)
| Professional Development |  |  | Unique portal access code
Resources |  |  |  | Unique registration link
About Us |  | https://pahp.underdogdigitalwebsite.com/about-us/ |  | Newsletter link (per portal)
Our Story
Meet the Team
Advisors
Contact
Schedule a Call
Sign In
Search
Setup the Main pages temalates
Set up the URL's
Remove the Unwanted URL's